BACKEND SCHEMA & IMPLEMENTATION PLAN

Multi-Tenant SaaS Booking System

Day-by-day build order · What to build, in what order, and why

# Part 1: Complete Database Schema

This is the authoritative schema. Copy it verbatim into packages/db/prisma/schema.prisma. Every field, index, and enum is here for a documented reason.

## 1.1 Full Prisma Schema

generator client {

provider = "prisma-client-js"

}

datasource db {

provider = "postgresql"

url      = env("DATABASE_URL")

}

// ─── TENANT ───────────────────────────────────────────────────

model Tenant {

id           String    @id @default(cuid())

name         String                          // "Dr. Anita's Clinic"

slug         String    @unique               // "dr-anita" → dr-anita.yourdomain.com

logoUrl      String?                         // Uploaded logo URL

primaryColor String    @default("#4F46E5")   // Tenant brand colour

plan         Plan      @default(FREE)

isActive     Boolean   @default(true)        // Super-admin can deactivate

createdAt    DateTime  @default(now())

updatedAt    DateTime  @updatedAt

users        User[]

services     Service[]

bookings     Booking[]

schedule     Schedule?

}

// ─── USER ─────────────────────────────────────────────────────

model User {

id            String   @id @default(cuid())

tenantId      String                         // FK — ties user to exactly one tenant

email         String   @unique

passwordHash  String                         // bcrypt 12 rounds — NEVER store plain text

name          String

role          Role     @default(STAFF)

isActive      Boolean  @default(true)

inviteToken   String?  @unique               // Set on invite, cleared on password set

inviteExpiry  DateTime?

lastLoginAt   DateTime?

createdAt     DateTime @default(now())

tenant        Tenant   @relation(fields: [tenantId], references: [id])

@@index([tenantId])                          // Every query filters by tenant first

}

// ─── SERVICE ──────────────────────────────────────────────────

model Service {

id          String    @id @default(cuid())

tenantId    String

name        String                           // "General Consultation"

description String?

duration    Int                              // Minutes: 15, 30, 45, 60, 90, 120

price       Float?                           // Null = no price shown to customer

sortOrder   Int       @default(0)            // Display order in booking flow

isActive    Boolean   @default(true)         // Soft delete — never hard delete

createdAt   DateTime  @default(now())

tenant      Tenant    @relation(fields: [tenantId], references: [id])

bookings    Booking[]

@@index([tenantId])

@@index([tenantId, isActive])                // Most queries filter active only

}

// ─── BOOKING ──────────────────────────────────────────────────

model Booking {

id              String        @id @default(cuid())

tenantId        String

serviceId       String

customerName    String

customerEmail   String

customerPhone   String?

startsAt        DateTime                     // Stored as UTC always

endsAt          DateTime                     // = startsAt + service.duration

status          BookingStatus @default(PENDING)

notes           String?                      // Customer notes at booking time

adminNotes      String?                      // Admin-only internal notes

cancelToken     String        @unique @default(cuid())  // For email cancel link

cancelReason    String?                      // Filled on cancellation

reminderSentAt  DateTime?                    // Null = reminder not yet sent

createdAt       DateTime      @default(now())

updatedAt       DateTime      @updatedAt

tenant          Tenant        @relation(fields: [tenantId], references: [id])

service         Service       @relation(fields: [serviceId], references: [id])

@@index([tenantId, startsAt])                // Primary query: tenant's bookings by date

@@index([tenantId, status])                  // Filtered views: pending, confirmed

@@index([cancelToken])                       // Cancel via email link lookup

@@index([reminderSentAt])                    // Cron job finds bookings needing reminder

}

// ─── SCHEDULE ─────────────────────────────────────────────────

model Schedule {

id           String   @id @default(cuid())

tenantId     String   @unique              // One schedule per tenant

timezone     String   @default("Asia/Kolkata")

workingDays  Json     // { mon:T, tue:T, wed:T, thu:T, fri:T, sat:T, sun:F }

workStart    String   @default("09:00")    // "HH:MM" 24hr format

workEnd      String   @default("18:00")

slotInterval Int      @default(30)         // Minutes between slot start times

breakTimes   Json     @default("[]")       // [{start:"13:00", end:"14:00"}]

bufferTime   Int      @default(0)          // Minutes after each booking before next slot

tenant       Tenant   @relation(fields: [tenantId], references: [id])

}

// ─── ENUMS ────────────────────────────────────────────────────

enum Role         { OWNER ADMIN STAFF }

enum Plan         { FREE PRO }

enum BookingStatus { PENDING CONFIRMED CANCELLED COMPLETED NO_SHOW }

## 1.2 RLS Setup Script

Save as packages/db/scripts/setup-rls.sql. Run after every production migration.

-- Enable RLS on all tenant-scoped tables

ALTER TABLE "User"     ENABLE ROW LEVEL SECURITY;

ALTER TABLE "Service"  ENABLE ROW LEVEL SECURITY;

ALTER TABLE "Booking"  ENABLE ROW LEVEL SECURITY;

ALTER TABLE "Schedule" ENABLE ROW LEVEL SECURITY;

-- Drop existing policies (idempotent re-run safe)

DROP POLICY IF EXISTS tenant_iso ON "User";

DROP POLICY IF EXISTS tenant_iso ON "Service";

DROP POLICY IF EXISTS tenant_iso ON "Booking";

DROP POLICY IF EXISTS tenant_iso ON "Schedule";

-- Create isolation policy for each table

CREATE POLICY tenant_iso ON "User"

USING ("tenantId" = current_setting('app.tenant_id', true));

CREATE POLICY tenant_iso ON "Service"

USING ("tenantId" = current_setting('app.tenant_id', true));

CREATE POLICY tenant_iso ON "Booking"

USING ("tenantId" = current_setting('app.tenant_id', true));

CREATE POLICY tenant_iso ON "Schedule"

USING ("tenantId" = current_setting('app.tenant_id', true));

-- VERIFICATION TEST (run manually to confirm RLS works):

-- SELECT set_config('app.tenant_id', 'tenant_a_id', true);

-- SELECT COUNT(*) FROM "Booking";  -- must return only tenant_a bookings

# Part 2: Implementation Plan — Day by Day

Realistic total: 70–100 hours across 35–50 days at 2 hours/day. The original 56-hour estimate assumed clean runs every session — that never happens in practice.

Honest hour breakdown:

• Backend (auth, API, availability engine, RLS): 25–35 hours

• Frontend (Next.js, booking flow, admin dashboard): 25–35 hours

• Email templates + Resend integration: 3–5 hours

• Deployment (DNS, Vercel, Railway, GitHub Actions): 3–5 hours

• Bug fixing and integration issues: 10–20 hours — this is NOT optional padding, this WILL happen

• Total: 70–100 hours. Set this expectation now so you do not feel like you are failing at week 5.

Rule: every day ends with something that runs.

• Not "I wrote some files" — the code must execute without crashing

• Commit at the end of every session, even if the feature is incomplete

• If you get stuck for more than 30 minutes, write the question down and move on — come back to it

• Platform: web-only. No mobile app work in any session. If you find yourself writing React Native or Expo code, stop.

## Week 1: Foundation — Monorepo, DB, Auth

| Day | Hours | Deliverable | Done When |
| --- | --- | --- | --- |
| 1 | 2hr | Monorepo scaffolded: pnpm workspaces, turbo.json, apps/web (Next.js), apps/api (Express), packages/db. All packages install without errors. | pnpm dev starts both apps with no errors |
| 2 | 2hr | Docker Compose running Postgres locally. Prisma schema created (copy from this doc). prisma migrate dev runs. Database tables created. | prisma studio opens and shows all tables empty |
| 3 | 2hr | RLS script applied to local DB. Seed script creates 2 tenants, 1 owner per tenant, 3 services per tenant. RLS verified: querying with tenant_a_id returns 0 rows for tenant_b data. | Verification SELECT returns 0 cross-tenant rows |
| 4 | 2hr | Express auth routes: POST /auth/register (creates Tenant + User). bcrypt hashing. POST /auth/login (returns JWT). POST /auth/refresh (rotates token). | curl /auth/login returns valid JWT |
| 5 | 2hr | Auth middleware: verifies JWT, sets req.user and req.tenantId, sets Postgres session variable for RLS. Applied to all /admin routes. | Protected route returns 401 without token, 200 with it |

## Week 2: Booking Engine + Public API

| Day | Hours | Deliverable | Done When |
| --- | --- | --- | --- |
| 6 | 2hr | Schedule CRUD: GET + PUT /admin/schedule. Default schedule auto-created on tenant registration. Returns correct JSON structure. | Postman: update schedule, GET returns new values |
| 7 | 2hr | Service CRUD: GET, POST, PUT, DELETE (soft) /admin/services. isActive filter on GET. sortOrder support. | Create 3 services via API, list returns all 3 |
| 8 | 2hr | Availability engine: getAvailableSlots() function written and unit tested. Test cases: closed day, fully booked, breaks, past slots, service duration overlap. | Jest: all availability test cases pass |
| 9 | 2hr | Public availability endpoint: GET /public/:slug/availability?serviceId&date. Fetches schedule + existing bookings for that day, runs availability engine, returns slots array. | curl returns correct slot array for tomorrow |
| 10 | 2hr | Public booking endpoint: POST /public/:slug/bookings. Validates slot still free (race condition check with SELECT FOR UPDATE). Creates booking. Triggers Resend confirmation email. | Create booking, receive confirmation email in inbox |

## Week 3: Admin Dashboard + Frontend

| Day | Hours | Deliverable | Done When |
| --- | --- | --- | --- |
| 11 | 2hr | Admin booking endpoints: GET /admin/bookings (with status + date filters), PATCH /admin/bookings/:id (status updates). Emails triggered on status change. | Confirm a booking via API, customer receives email |
| 12 | 2hr | Next.js middleware for subdomain routing. Test with clinic.localhost:3000 and salon.localhost:3000 in /etc/hosts. Both resolve to correct tenant. | Two different tenants load at two subdomains locally |
| 13 | 2hr | Public booking flow UI: service list page → date picker → time slot picker. Mobile-first. Connects to live API. | Complete a booking end-to-end through the browser |
| 14 | 2hr | Customer details form + confirmation page. Cancel via email link flow (GET + POST /public/bookings/cancel/:token). | Cancel a booking via email link, status updates to CANCELLED |
| 15 | 2hr | Admin login + dashboard home. JWT stored in React state. Auth token refresh on 401. KPI cards + upcoming bookings list. | Log in, see today's bookings on dashboard |

## Week 4: Polish, Emails, Deploy

| Day | Hours | Deliverable | Done When |
| --- | --- | --- | --- |
| 16 | 2hr | Admin booking management UI: list with filters, slide-over detail panel, confirm/cancel actions with optimistic updates. | Admin can confirm and cancel bookings from the UI |
| 17 | 2hr | Services and Schedule management UI. Service CRUD. Schedule form with working days toggles, time pickers, break window manager. | Admin can add a service and change schedule from the UI |
| 18 | 2hr | React Email templates for all 5 email types. Templates look professional in Gmail/Outlook. .ics calendar attachment on confirmation email. | All 5 email types received and look correct in Gmail |
| 19 | 2hr | Staff invite flow: send invite email, accept-invite endpoint, role-restricted dashboard for STAFF role. Branding settings page (logo upload, colour picker). | Invite a staff member, they log in with restricted access |
| 20 | 2hr | Deploy: wildcard DNS on domain, Vercel (frontend), Railway (API + Postgres), CI/CD GitHub Actions (test → migrate → deploy). Seed production DB. | Live at yourname-booking.com with two demo tenants |
| 21+ | 10–20hr BUFFER | Bug fixing, integration issues, unexpected blockers. This is NOT optional padding — DNS propagation alone can take 48hrs. Prisma migration issues, NextAuth subdomain cookie edge cases, and Resend deliverability debugging are all common. | All items in the testing checklist below pass |

## Critical Implementation Notes

### Race Condition on Booking Creation — Requires Both Locking AND Serializable Isolation

Between a customer selecting a slot and submitting the form, another customer could book the same slot. SELECT FOR UPDATE alone is not sufficient — SERIALIZABLE isolation level is also required. Without it, two transactions can both pass the conflict check before either commits.

// apps/api/src/routes/bookings.ts

await prisma.$transaction(

async (tx) => {

// SELECT FOR UPDATE: locks conflicting rows

// SKIP LOCKED: treats already-locked rows as conflicts immediately

const conflict = await tx.$queryRaw`

SELECT id FROM "Booking"

WHERE "tenantId"  = ${tenantId}

AND status NOT IN ('CANCELLED')

AND "startsAt" < ${endsAt}

AND "endsAt"   > ${startsAt}

FOR UPDATE SKIP LOCKED

`;

if (conflict.length > 0) {

throw new Error('SLOT_TAKEN');  // → 409 response

}

return tx.booking.create({ data: { ...bookingData } });

},

{ isolationLevel: 'Serializable' }  // ← mandatory — without this, race condition still possible

);

### All Times Stored as UTC

The Schedule model stores workStart and workEnd as "HH:MM" strings in the tenant's local timezone. All Booking.startsAt and endsAt are stored as UTC DateTime in Postgres. The availability engine converts using date-fns-tz. Never store local time in the database.

### Email Failures Must Not Fail the Booking

Wrap all Resend calls in try-catch. A booking must be created even if the email fails. Log the failure and implement a retry mechanism — the simplest approach is a cron job that checks for bookings created in the last hour with no confirmation email sent (add a confirmationEmailSentAt column).

## Testing Checklist Before Demo

Run through every item before showing to any client or hiring manager:

• 1. Create a new tenant at yourdomain.com/register — verify subdomain works

• 2. Add 3 services, configure schedule with a lunch break

• 3. Complete a full customer booking in a real mobile phone browser (375px) — verify email received with .ics

• 4. Admin logs in, confirms the booking — verify customer receives confirmation email

• 5. Cancel via email link — verify status updates and both customer + admin receive cancellation emails

• 6. Invite a staff member — verify they log in with restricted access (no Services/Schedule tabs)

• 7. Create two tenants, confirm Tenant A cannot see Tenant B's bookings — this is the RLS verification

• 8. Run concurrent booking test: 50 simultaneous requests to same slot — verify exactly 1 succeeds. DO NOT claim double-booking prevention without passing this test.

• 9. Temporarily disable Resend API key — verify booking still creates (email failure must not block booking)

• 10. Check all emails render correctly in Gmail on a real mobile phone

• 11. Confirm there is zero React Native, Expo, or app store code in the repository — all three projects are web-only

• 12. First outreach target: personal trainer, yoga studio, tutor, photographer, or consultant — not a clinic

— End of Backend Schema & Implementation Plan —