FEATURE BUILD GUIDE

BookingOS · booking.virajdomadia.com

12 features · ~83 hours · project setup to production

How to use this document

Each feature is a vertical slice — it touches DB, API, and frontend together.

Build features in order. Each feature has a DONE WHEN section — do not move to the

next feature until every item in it passes. This is how you avoid carrying forward

broken assumptions that cost 3x the time to fix later.

Time estimates are per feature, not per day. Work at your own pace.

When stuck for more than 30 minutes — write the question, move to a smaller task within

the same feature, come back to the blocker fresh.

# Feature Overview

| ID | Feature | Est. | Depends On | Layer |
| --- | --- | --- | --- | --- |
| F0 | Project Setup & Infrastructure | 6–8 hrs | None | DB + Config |
| F1 | Auth — Register, Login, Tokens | 8–10 hrs | F0 | DB + API + UI |
| F2 | Tenant & Schedule Management | 6–8 hrs | F1 | API + UI |
| F3 | Service Management | 4–6 hrs | F1 | API + UI |
| F4 | Public Booking Flow | 14–18 hrs | F2 + F3 | API + UI |
| F5 | Admin Booking Management | 8–10 hrs | F4 | API + UI |
| F6 | Email Notifications | 6–8 hrs | F4 + F5 | API + Email |
| F7 | Customer Cancel via Email Link | 4–5 hrs | F6 | API + UI |
| F8 | Staff Management | 5–6 hrs | F1 + F6 | API + UI |
| F9 | 24hr Reminder Cron | 2–3 hrs | F6 | API |
| F10 | Super Admin Panel | 4–5 hrs | F1 | API + UI |
| F11 | Deploy & Go Live | 6–8 hrs | All | DevOps |

Total realistic estimate: 73–87 hours. Add 10–20 hours bug-fixing buffer from the implementation plan = 83–107 hours total.

| F0 | Project Setup & Infrastructure | Est. 6–8 hrs | Needs None |
| --- | --- | --- | --- |

Everything that must exist before a single line of application code runs. Get this right once and never touch it again.

MONOREPO & TOOLING

- Init repo: git init, create root package.json with pnpm workspaces

- Create pnpm-workspace.yaml pointing to apps/* and packages/*

- Scaffold folders: apps/web (Next.js 14), apps/api (Express), packages/db, packages/types, packages/utils

- Root package.json scripts: dev (concurrently), dev:api, dev:web, db:migrate, db:studio

- TypeScript config: root tsconfig.json with path aliases, each app/package extends it

- Install concurrently at root for running both apps simultaneously

DATABASE

- docker-compose.yml: Postgres 15 container, port 5432, named volume for persistence

- packages/db: Prisma schema (copy from 05_Schema_ImplPlan.docx verbatim)

- packages/db: package.json with prisma commands (migrate, studio, generate)

- Run prisma migrate dev — verify all 5 tables created (Tenant, User, Service, Booking, Schedule)

- packages/db/scripts/rls.sql — copy from 06_Security_Access.docx

- Apply RLS script to local DB: psql $DATABASE_URL < packages/db/scripts/rls.sql

SEED DATA

- packages/db/seed.ts — creates 2 tenants (demo-clinic, demo-salon)

- Each tenant: 1 owner user (bcrypt hashed password), 3 services, 1 schedule (defaults)

- Use realistic names: Dr. Anita's Clinic / Style Studio

- Run seed: pnpm --filter db seed

- Verify in Prisma Studio: both tenants visible, services correct, schedules present

ENVIRONMENT VARIABLES

- Create .env.example at repo root documenting all required variables

- Create .env files in apps/api and apps/web (gitignored)

- Generate secrets: openssl rand -hex 32 for JWT_SECRET and JWT_REFRESH_SECRET

- Verify DATABASE_URL connects: npx prisma db pull should succeed

RLS VERIFICATION (CRITICAL — DO NOT SKIP)

- Open psql or any Postgres client connected to local DB

- Run: SELECT set_config('app.tenant_id', '<demo-clinic-id>', true);

- Run: SELECT COUNT(*) FROM "Booking" WHERE "tenantId" = '<demo-salon-id>';

- Expected result: 0. If result > 0, RLS is not applied — re-run rls.sql before proceeding

DONE WHEN — all of these pass before moving to next feature

✓ pnpm dev starts both apps/web (port 3000) and apps/api (port 4000) with no errors

✓ Prisma Studio opens and shows Tenant, User, Service, Booking, Schedule tables with seed data

✓ RLS cross-tenant query returns 0 rows

✓ .env.example documents every variable, .env files are gitignored

✓ docker compose up starts Postgres, docker compose down stops it cleanly

| F1 | Auth — Register, Login, Token Flow | Est. 8–10 hrs | Needs F0 |
| --- | --- | --- | --- |

The auth system is the skeleton everything else attaches to. Custom JWT on Express only — no NextAuth. Get this right before building any protected feature.

EXPRESS API — AUTH ROUTES

- POST /auth/register

- Validate body with Zod: businessName, slug, email, password

- Check slug uniqueness (return 409 if taken)

- Check email uniqueness (return 409 if taken)

- Create Tenant, User (OWNER, bcrypt 12 rounds), default Schedule in a Prisma transaction

- Return access token + set refresh cookie

- POST /auth/login

- Find user by email, compare bcrypt hash

- Issue JWT access token (15min, payload: { userId, tenantId, role })

- Generate opaque refresh token UUID, store in DB with 7-day expiry

- Set httpOnly Secure SameSite=Strict cookie (domain: .virajdomadia.com in prod, undefined locally)

- POST /auth/refresh

- Read refresh_token cookie

- Find in DB, verify not expired

- Delete old token, create new one (rotation)

- Issue new access token, set new cookie

- POST /auth/logout — delete refresh token from DB, clear cookie

EXPRESS — AUTH MIDDLEWARE

- authMiddleware: extract Bearer token, jwt.verify, set req.user and req.tenantId

- Set Postgres RLS context: SELECT set_config('app.tenant_id', ${tenantId}, true)

- Return 401 if no token, 401 if invalid/expired

- Apply to all /admin/* routes

- requireRole(...roles) middleware: check req.user.role, return 403 if insufficient

NEXT.JS FRONTEND — AUTH

- AuthContext (apps/web/src/context/auth.tsx)

- State: accessToken (string|null), user ({userId, tenantId, role}|null)

- Actions: login(), logout(), silentRefresh()

- useEffect on mount: attempt silentRefresh() so page refresh keeps user logged in

- Axios instance (apps/web/src/lib/api.ts)

- baseURL: NEXT_PUBLIC_API_URL, withCredentials: true

- Request interceptor: attach Authorization: Bearer <token> header

- Response interceptor: on 401, call /auth/refresh, retry original request

- On refresh failure: redirect to /book/[slug]/admin/login

- Admin login page: /book/[slug]/admin/login

- Email + password form, single column

- On submit: call login(), redirect to /book/[slug]/admin on success

- Error state: 'Invalid email or password' inline message

- Route guard: /book/[slug]/admin/* pages check AuthContext, redirect to login if no token

RATE LIMITING

- Install express-rate-limit

- POST /auth/login: max 10 requests per 15 minutes per IP

- POST /auth/register: max 5 requests per 60 minutes per IP

DONE WHEN — all of these pass before moving to next feature

✓ curl POST /auth/register creates tenant, returns JWT, sets httpOnly cookie

✓ curl POST /auth/login with wrong password returns 401

✓ curl GET /admin/bookings without token returns 401

✓ curl GET /admin/bookings with valid token returns 200 (empty array is fine)

✓ Refresh token visible in browser DevTools cookies as httpOnly — not readable via document.cookie

✓ Page refresh on /book/demo-clinic/admin stays logged in (silentRefresh working)

✓ 11 rapid login attempts from same IP: 11th returns 429

✓ RLS context set: console.log(req.tenantId) in a protected route prints correct tenant ID

| F2 | Tenant & Schedule Management | Est. 6–8 hrs | Needs F1 |
| --- | --- | --- | --- |

The schedule is the source of truth for availability. Nothing in F4 (booking flow) works correctly until the schedule is configurable and saved properly.

EXPRESS API — SCHEDULE

- GET /admin/schedule — return tenant's schedule (created by default in F1 registration)

- PUT /admin/schedule — update all schedule fields

- Validate with Zod: workingDays object, workStart/workEnd HH:MM strings, slotInterval number, breakTimes array, bufferTime number, timezone string

- Validate workStart < workEnd

- Validate break times don't overlap each other

- GET /admin/tenant — return tenant name, logoUrl, primaryColor

- PUT /admin/tenant — update name, logoUrl, primaryColor

NEXT.JS FRONTEND — SCHEDULE SETTINGS

- Schedule settings page: /book/[slug]/admin/schedule

- Working days: 7 toggle chips (Mon–Sun), active = brand colour, inactive = grey

- Work start / work end: time picker inputs (HH:MM, 15-min increments)

- Slot interval: dropdown (15 / 30 / 45 / 60 min)

- Buffer time: dropdown (0 / 5 / 10 / 15 min)

- Break windows manager:

- List of existing breaks with delete button

- 'Add Break' button → two time pickers (start, end) + confirm

- Validate: break end must be after break start

- Save button: PUT /admin/schedule, success toast, error toast on failure

- Unsaved changes warning: if user navigates away with unsaved changes, show browser confirm dialog

EXPRESS API — TENANT BRANDING

- PUT /admin/tenant: update name, primaryColor

- Logo upload: accept multipart/form-data, store as base64 string in logoUrl (V1 simplification — no S3)

NEXT.JS FRONTEND — BRANDING SETTINGS

- Branding settings page: /book/[slug]/admin/settings

- Business name input

- Primary colour: hex input + colour swatch preview

- Logo upload: file input, preview thumbnail after selection

- Save: PUT /admin/tenant

DONE WHEN — all of these pass before moving to next feature

✓ GET /admin/schedule returns default schedule (Mon–Sat, 09:00–18:00, 30min slots)

✓ Update schedule via UI: change Tuesday to OFF, save, reload page — Tuesday still OFF

✓ Add a lunch break 13:00–14:00, save — break persists on reload

✓ Update primary colour, save — colour updates in UI immediately

✓ Invalid schedule (workEnd before workStart) shows validation error, does not save

| F3 | Service Management | Est. 4–6 hrs | Needs F1 |
| --- | --- | --- | --- |

Services are what customers book. Simple CRUD but the isActive soft-delete and sortOrder fields matter for the booking flow.

EXPRESS API — SERVICES

- GET /admin/services — return all services for tenant (active and inactive), ordered by sortOrder

- POST /admin/services — create service

- Zod validation: name (required), description (optional), duration (15|30|45|60|90|120), price (optional float), sortOrder (default: count of existing + 1)

- PUT /admin/services/:id — update any field

- DELETE /admin/services/:id — soft delete: set isActive = false (never hard delete — bookings reference services)

- PATCH /admin/services/:id/restore — set isActive = true

NEXT.JS FRONTEND — SERVICES

- Services list page: /book/[slug]/admin/services

- Two sections: Active Services, Inactive Services (collapsed by default)

- Each service row: name, duration badge, price (if set), edit button, deactivate button

- 'Add Service' button → slide-over panel from right

- Fields: Name, Description (textarea), Duration (dropdown), Price (optional, with currency label)

- POST /admin/services on submit, new service appears at bottom of list

- Edit button → same slide-over pre-filled with existing data, PUT on submit

- Deactivate: confirm modal ('Customers won't be able to book this service. Existing bookings are unaffected.'), then DELETE

- Empty state: 'No services yet — add your first service to start accepting bookings'

DONE WHEN — all of these pass before moving to next feature

✓ Create 3 services via UI, all appear in list with correct duration and price

✓ Edit a service name, save, reload — new name persists

✓ Deactivate a service — it moves to Inactive section, no longer appears in GET /public/:slug/services

✓ Attempt to create service with no name — inline validation error, form does not submit

✓ GET /public/demo-clinic/services returns only active services (test via curl before F4)

| F4 | Public Booking Flow | Est. 14–18 hrs | Needs F2 + F3 |
| --- | --- | --- | --- |

The most important feature. This is what customers use. Every edge case here costs you a real booking if you ship it wrong. Build it slowly. Test it on a real mobile phone before marking done.

AVAILABILITY ENGINE (PACKAGES/UTILS)

- getAvailableSlots(date, schedule, existingBookings, serviceDuration): SlotArray

- Return empty array if date is a closed working day

- Generate slots from workStart to workEnd at slotInterval increments

- Filter: skip past slots (slot start <= now)

- Filter: skip booked slots (overlap check: cursor < b.endsAt && slotEnd > b.startsAt)

- Filter: skip break time slots (same overlap check against breakTimes array)

- Apply bufferTime: treat each existing booking as endsAt + bufferTime for overlap check

- All times converted using date-fns-tz with schedule.timezone

- Unit tests (Jest) — all must pass before building the API endpoint:

- Returns empty array for a closed day

- Returns empty array when all slots are booked

- Lunch break (13:00–14:00) blocks correct slots

- Past slots not returned (mock 'now' to a fixed time)

- 60-minute service only fits in correct slots given slot interval

- Buffer time adds gap after existing bookings

EXPRESS API — PUBLIC ENDPOINTS

- GET /public/:slug/services

- Find tenant by slug — return 404 if not found or isActive=false

- Return active services + tenant branding (name, logoUrl, primaryColor)

- GET /public/:slug/availability?serviceId=X&date=YYYY-MM-DD

- Fetch schedule for tenant

- Fetch existing bookings for that date (status NOT IN CANCELLED)

- Run getAvailableSlots(), return array of {start, end} in ISO strings

- Return empty array (not 404) if no slots available

- POST /public/:slug/bookings

- Zod validation: serviceId, startsAt (ISO datetime), customerName, customerEmail, customerPhone (optional), notes (optional)

- Calculate endsAt = startsAt + service.duration

- SERIALIZABLE transaction + SELECT FOR UPDATE SKIP LOCKED conflict check

- Return 409 { error: 'SLOT_TAKEN' } if conflict found

- Create booking, trigger confirmation email (non-blocking try-catch)

- Return created booking with id and cancelToken

NEXT.JS FRONTEND — BOOKING PAGES

- Service list page: /book/[slug]/page.tsx

- Fetch tenant branding + services from /public/:slug/services

- Show tenant logo + name in header

- Service list: full-width tap targets, min 56px height, name + duration + price

- Loading skeleton: 3 grey pill-height blocks

- 404 state: tenant not found or inactive

- Date picker page: /book/[slug]/[serviceId]/date/page.tsx

- Calendar grid (custom, not native input — Android native is inconsistent)

- Past dates disabled (grey)

- Prefetch availability for next 14 days to grey out fully-booked dates

- Selected date highlighted in brand colour

- Slot picker page: /book/[slug]/[serviceId]/slots/page.tsx

- Fetch /public/:slug/availability?serviceId&date on mount

- Loading skeleton: 4 grey pill shapes in 2-column grid

- Slot pills in 2-column grid, JetBrains Mono font for times

- Empty state: 'No times available on [date] — try another day' with back link

- Selected slot highlighted

- Customer details page: /book/[slug]/[serviceId]/details/page.tsx

- Single column form: Name (required), Email (required), Phone (optional — labelled), Notes (optional — labelled)

- Inline validation on blur (not on submit)

- No asterisks — optional fields explicitly labelled '(optional)'

- Submit: POST /public/:slug/bookings

- 409 response: 'This slot was just taken — choose another time.' → redirect back to slots page

- Confirmation page: /book/[slug]/[serviceId]/confirm/page.tsx

- Full-screen success state — not a toast

- Booking summary card: service, date, time, name, email

- Unique booking reference (booking.id truncated to 8 chars)

- 'Add to calendar' hint (email has the .ics)

CRITICAL UX REQUIREMENTS

- Each step is a real URL — browser back button navigates correctly through all steps

- State is passed via URL params or sessionStorage — not React state that dies on back navigation

- Tenant branding (primaryColor) applied to CTA buttons and selected states

- All pages work at 375px viewport — test in real phone browser, not DevTools

DONE WHEN — all of these pass before moving to next feature

✓ All 6 availability engine unit tests pass (npx jest)

✓ Complete booking end-to-end in a real mobile phone browser — not DevTools emulation

✓ Browser back button from each step returns to previous step correctly

✓ Fully-booked date shows as grey in calendar

✓ Empty availability returns 'No times available' message, not a blank page

✓ Submit booking, immediately submit same slot in another tab — second gets 'slot just taken' message

✓ Confirmation page shows correct booking details

✓ GET /public/demo-clinic/services returns 404 for a slug that does not exist

| F5 | Admin Booking Management | Est. 8–10 hrs | Needs F4 |
| --- | --- | --- | --- |

The admin's primary daily tool. Design for speed — Dr. Anita should be able to confirm her morning bookings in under 2 minutes.

EXPRESS API — ADMIN BOOKINGS

- GET /admin/bookings

- Query params: status (optional), date (optional, YYYY-MM-DD), serviceId (optional), page (default 1), limit (default 20)

- Include: service name, customer details

- Order by startsAt ASC

- GET /admin/bookings/today — shortcut for today's bookings (used by dashboard KPIs)

- PATCH /admin/bookings/:id

- status: CONFIRMED — allowed from PENDING only

- status: CANCELLED — allowed from PENDING or CONFIRMED. Require cancelReason in body.

- status: COMPLETED — allowed from CONFIRMED only

- status: NO_SHOW — allowed from CONFIRMED only

- adminNotes: update internal notes (any status)

- Trigger appropriate email on status change (non-blocking)

NEXT.JS FRONTEND — DASHBOARD HOME

- Dashboard home: /book/[slug]/admin/page.tsx

- 4 KPI cards (top row):

- Today's Bookings (count)

- This Week (count)

- Pending Confirmation (count, amber if > 0)

- Next Booking (time + customer name, or 'None today')

- Upcoming bookings list (next 5): time, customer name, service, status badge

- Quick actions: 'View all bookings' link

- Loading: skeleton cards matching KPI shape

NEXT.JS FRONTEND — BOOKINGS LIST

- Bookings list page: /book/[slug]/admin/bookings/page.tsx

- Filter bar: date range picker, status chips (All | Pending | Confirmed | Cancelled | Completed), service dropdown

- Table columns: Time, Customer Name, Service, Status Badge, Actions

- Status badges: Pending (amber), Confirmed (green), Cancelled (red), Completed (grey), No-Show (grey)

- confirmationEmailStatus badge: small dot on row if email FAILED

- Pagination: previous/next, show 'X–Y of Z bookings'

- Click any row → slide-over panel from right (do not navigate to new page)

NEXT.JS FRONTEND — BOOKING DETAIL SLIDE-OVER

- Customer: name, email, phone (click to copy), notes

- Booking: service, date, time, duration, booking reference, created at

- Status badge + current status

- Admin notes: textarea, auto-saves on blur

- Action buttons (shown based on current status):

- PENDING: 'Confirm Booking' (green), 'Cancel' (red)

- CONFIRMED: 'Mark Complete' (grey), 'Mark No-Show' (grey), 'Cancel' (red)

- CANCELLED / COMPLETED / NO_SHOW: no action buttons

- Cancel action: modal with reason textarea (optional), confirm button

- Optimistic updates: badge changes immediately, API fires in background, reverts on failure with error toast

DONE WHEN — all of these pass before moving to next feature

✓ Dashboard KPIs show correct counts for seed data bookings

✓ Filter by status=PENDING returns only pending bookings

✓ Confirm a booking from UI — status badge updates immediately (optimistic), API call succeeds

✓ Cancel a booking with reason — status updates, cancelReason stored in DB

✓ Admin notes save on blur — reload page, notes still there

✓ Email failure badge visible on a booking where confirmationEmailStatus=FAILED

✓ Attempting to confirm a CANCELLED booking returns 400 (invalid transition)

| F6 | Email Notifications | Est. 6–8 hrs | Needs F4 + F5 |
| --- | --- | --- | --- |

Email is the only communication channel with customers. Every email must look professional and render correctly on mobile Gmail. Build all templates before wiring any of them up.

REACT EMAIL TEMPLATES (APPS/API/SRC/EMAILS/)

- booking-confirmation.tsx — sent to customer when booking created

- Content: service name, date, time, customer name, booking reference, cancel link

- .ics calendar attachment (see below)

- booking-confirmed.tsx — sent to customer when admin confirms

- Content: 'Your booking is confirmed', same booking details

- booking-cancelled.tsx — sent to customer when cancelled (by admin or self)

- Content: 'Your booking has been cancelled', cancelReason if present, rebook link

- booking-reminder.tsx — 24hr before appointment (sent by cron in F9)

- Content: reminder of date/time, cancel link, 'see you tomorrow' tone

- admin-new-booking.tsx — sent to tenant owner when new booking created

- Content: customer name, service, date/time, phone, notes

- admin-cancellation.tsx — sent to tenant owner when booking cancelled

- Content: customer name, which booking, cancel reason

- staff-invite.tsx — sent when owner invites a staff member (used in F8)

- Content: inviter name, business name, set-password link with invite token

.ICS CALENDAR ATTACHMENT

- Install ical-generator package

- Generate .ics content for each booking: summary (service name), dtstart, dtend, location (business name), description (booking reference)

- Attach to booking-confirmation email as base64 encoded attachment

- Test: .ics file opens correctly in Google Calendar and iPhone Calendar

EMAIL SERVICE (APPS/API/SRC/SERVICES/EMAIL.TS)

- Single sendEmail(type, data) function — all email sends go through here

- Every call wrapped in try-catch — email failure NEVER throws

- On success: update booking.confirmationEmailStatus = 'SENT' (for confirmation emails)

- On failure: update booking.confirmationEmailStatus = 'FAILED', console.error with booking ID

- Send confirmation email immediately after booking creation (in POST /public/:slug/bookings)

- Send admin-new-booking email immediately after booking creation

- Send booking-confirmed email after PATCH status to CONFIRMED

- Send booking-cancelled email (to customer AND admin) after PATCH status to CANCELLED

RESEND CONFIGURATION

- RESEND_API_KEY in apps/api .env

- From address: bookings@yourdomain.com (must match verified Resend domain)

- Verify Resend domain DNS records before testing — takes up to 24hrs

DONE WHEN — all of these pass before moving to next feature

✓ Create a booking — confirmation email received in inbox within 30 seconds

✓ .ics attachment opens in Google Calendar with correct date, time, and event name

✓ Confirm a booking from admin — customer receives confirmed email

✓ Cancel a booking from admin — customer AND admin receive cancellation emails

✓ All 6 email types render correctly in Gmail on a real mobile phone (not DevTools)

✓ Temporarily set RESEND_API_KEY to an invalid value — booking still creates, confirmationEmailStatus = FAILED in DB

✓ Admin dashboard shows email failure badge on the booking from above test

| F7 | Customer Cancel via Email Link | Est. 4–5 hrs | Needs F6 |
| --- | --- | --- | --- |

Customers cancel themselves. This reduces admin workload and is a key selling point. The cancelToken is the only authentication needed.

EXPRESS API

- GET /public/bookings/cancel/:token

- Find booking by cancelToken

- Return 404 { error: 'INVALID_TOKEN' } if not found

- Return booking details: service name, date/time, customer name, status

- POST /public/bookings/cancel/:token

- Find booking by cancelToken

- Return 404 if not found

- Return 400 { error: 'ALREADY_CANCELLED' } if status is already CANCELLED

- Return 400 { error: 'CANNOT_CANCEL' } if status is COMPLETED or NO_SHOW

- Update status to CANCELLED, set cancelReason = 'Cancelled by customer'

- Send booking-cancelled email to customer and admin (non-blocking)

NEXT.JS FRONTEND

- Cancel page: /cancel/[token]/page.tsx

- On load: GET /public/bookings/cancel/:token

- Loading state: spinner

- Invalid token: 'This cancellation link is invalid or has already been used.'

- Already cancelled: 'This booking is already cancelled.'

- Valid: show booking summary card + single large 'Cancel this booking' button

- On confirm: POST /public/bookings/cancel/:token

- Success: 'Your booking has been cancelled.' + 'Book again' link back to service list

- Error: generic error message + 'contact us' fallback

- No login required — the cancel page is fully public

DONE WHEN — all of these pass before moving to next feature

✓ Click cancel link in confirmation email — cancel page loads with correct booking details

✓ Confirm cancellation — status updates to CANCELLED in DB

✓ Both customer and admin receive cancellation emails

✓ Click same cancel link again — 'already cancelled' message, no duplicate processing

✓ Manually change token in URL to a random string — 'invalid link' message, 404 from API

✓ 'Book again' link goes back to the correct tenant's service list

| F8 | Staff Management | Est. 5–6 hrs | Needs F1 + F6 |
| --- | --- | --- | --- |

Staff accounts let the business owner delegate booking management without giving away full admin access. Role restrictions are enforced both on the API and in the UI.

EXPRESS API

- POST /admin/staff/invite

- requireRole('OWNER', 'ADMIN')

- Zod: email (required), role (ADMIN | STAFF)

- Check: email not already a user in this tenant (409 if exists)

- Create User with role, isActive=false, inviteToken (cuid()), inviteExpiry (48hrs from now)

- Send staff-invite email with link: /accept-invite/[inviteToken]

- POST /auth/accept-invite

- Zod: token (required), password (required, min 8 chars)

- Find user by inviteToken

- Return 400 if token not found, expired, or already used

- Set passwordHash (bcrypt), isActive=true, clear inviteToken and inviteExpiry

- Return access token + set refresh cookie (user is now logged in)

- GET /admin/staff — list all users for tenant (id, name, email, role, isActive, lastLoginAt)

- PATCH /admin/staff/:id

- requireRole('OWNER', 'ADMIN')

- Can update: role, isActive

- Cannot demote or deactivate the OWNER account

- Cannot change own role

NEXT.JS FRONTEND — STAFF PAGE

- Staff page: /book/[slug]/admin/staff/page.tsx

- Only visible to OWNER and ADMIN roles (hide from STAFF)

- Staff list: name, email, role badge, active status, last login

- 'Invite Staff' button → slide-over: email input + role dropdown (Admin / Staff) + send button

- Deactivate toggle: confirm modal, PATCH isActive=false

- Role change dropdown: inline, PATCH on change

ROLE-RESTRICTED DASHBOARD (STAFF ROLE)

- STAFF users see: Bookings list + detail (view, confirm, complete, add notes only)

- STAFF users do NOT see: Services, Schedule, Staff, Settings nav items

- STAFF users cannot cancel bookings (button hidden in UI, 403 from API)

- Enforce both in the UI (hide elements) AND in the API (requireRole middleware)

ACCEPT INVITE PAGE

- Accept invite page: /accept-invite/[token]/page.tsx

- On load: validate token exists (GET /auth/accept-invite/:token for validation only)

- Invalid/expired token: 'This invitation link is invalid or has expired.'

- Valid: show 'Set your password' form (password + confirm password)

- On submit: POST /auth/accept-invite, redirect to admin dashboard on success

DONE WHEN — all of these pass before moving to next feature

✓ Owner invites staff via UI — invite email received within 30 seconds

✓ Staff clicks link, sets password, is redirected to admin dashboard

✓ Staff dashboard: Services, Schedule, Staff, Settings nav items are hidden

✓ Staff attempts DELETE /admin/services/:id via curl with staff JWT — returns 403

✓ Invite the same email twice — second invite returns 409 conflict

✓ Use an expired invite link (manually set inviteExpiry in past) — error shown

✓ Owner deactivates staff account — staff JWT returns 401 on next request

| F9 | 24hr Reminder Cron | Est. 2–3 hrs | Needs F6 |
| --- | --- | --- | --- |

The cron job runs inside the Express process using node-cron. No Redis, no external queue. Simple and sufficient for V1.

IMPLEMENTATION

- Install node-cron

- Create apps/api/src/jobs/reminder.ts

- Schedule: runs every hour (cron: '0 * * * *')

- Query: find bookings where

- status = CONFIRMED

- reminderSentAt IS NULL

- startsAt is between NOW + 20 hours and NOW + 28 hours

- (8-hour window prevents double-sending if cron runs slightly early/late)

- For each booking: send booking-reminder email, set reminderSentAt = now()

- Wrap entire job in try-catch — cron failure must not crash Express process

- Log: 'Reminder sent for booking [id]' on success, error log on failure

- Register cron job in apps/api/src/app.ts on server start

DONE WHEN — all of these pass before moving to next feature

✓ Create a confirmed booking with startsAt = now + 24 hours

✓ Manually trigger reminder job (export and call directly in a test script)

✓ Reminder email received in inbox

✓ reminderSentAt field set on booking in DB

✓ Run trigger again — no second email sent (reminderSentAt IS NULL filter prevents it)

| F10 | Super Admin Panel | Est. 4–5 hrs | Needs F1 |
| --- | --- | --- | --- |

Your operator dashboard. You use this to manage tenants. Separate from tenant admin — super admin can see all tenants, tenant admins see only their own data.

SCHEMA ADDITION

- Add isSuperAdmin: Boolean @default(false) to User model

- Create migration: prisma migrate dev --name add_super_admin

- Add one super admin user to seed script (or create via direct DB insert)

EXPRESS API

- Super admin middleware: check req.user.isSuperAdmin === true, return 403 if not

- GET /superadmin/tenants

- Return: id, name, slug, plan, isActive, createdAt, user count, booking count

- Order by createdAt DESC

- PATCH /superadmin/tenants/:id

- Toggle isActive (activate/deactivate)

- Deactivating a tenant: their public booking pages return 404, admin login still works

NEXT.JS FRONTEND

- Super admin login: /superadmin/login — separate from tenant admin login

- Super admin dashboard: /superadmin/page.tsx

- Table: tenant name, slug (as link to booking page), plan badge, status badge, created date, booking count

- Activate/deactivate toggle per row

- Search/filter by name or slug

- No tenant branding applied to super admin panel — plain system UI

DONE WHEN — all of these pass before moving to next feature

✓ Super admin can log in at /superadmin/login

✓ Tenant list shows both demo tenants with correct booking counts

✓ Deactivate demo-clinic — /book/demo-clinic returns 404

✓ Reactivate demo-clinic — /book/demo-clinic works again

✓ Tenant admin JWT cannot access /superadmin/* routes (returns 403)

| F11 | Deploy & Go Live | Est. 6–8 hrs | Needs All features |
| --- | --- | --- | --- |

Do not start this until every previous feature is working locally. Fixing bugs through a deployment pipeline is 3x slower than fixing them locally.

PRE-DEPLOY CHECKLIST (RUN LOCALLY FIRST)

- All items in 07_PreDev_Setup.docx readiness checklist pass

- Complete booking flow on real mobile phone (not DevTools)

- Concurrent booking test: 50 simultaneous POST requests to same slot — exactly 1 succeeds

- RLS cross-tenant verification passes

- All email types received and render correctly on mobile Gmail

RAILWAY — EXPRESS API

- Create Railway project, add Postgres database plugin

- Deploy apps/api from GitHub (Railway detects Node.js automatically)

- Set all environment variables in Railway dashboard (DATABASE_URL auto-set by plugin)

- Run migrations on production DB: railway run pnpm --filter db migrate

- Run RLS script on production DB: railway run psql $DATABASE_URL < packages/db/scripts/rls.sql

- Run seed script: railway run pnpm --filter db seed

- Verify: curl https://api.railway.app/auth/login returns expected response

VERCEL — NEXT.JS FRONTEND

- Import GitHub repo in Vercel, set root directory to apps/web

- Set environment variables in Vercel dashboard (NEXT_PUBLIC_API_URL = Railway URL)

- Add custom domain: booking.virajdomadia.com

- In DNS provider: add CNAME record booking → cname.vercel-dns.com

- Wait for DNS propagation (up to 48hrs, usually <1hr on Cloudflare)

- Verify SSL cert issued: https://booking.virajdomadia.com loads without security warning

GITHUB ACTIONS CI/CD

- Create .github/workflows/deploy.yml

- Trigger: push to main branch

- Steps: install → type check → run tests → prisma migrate deploy → run rls.sql → deploy to Railway + Vercel

- Add Railway and Vercel tokens as GitHub secrets

- Verify: push a commit, watch Actions run, confirm deployment succeeds

POST-DEPLOY VERIFICATION (RUN EVERY ITEM)

- Full booking flow on real mobile at booking.virajdomadia.com/book/demo-clinic

- Admin login, confirm a booking, check email received

- Cancel via email link, check status updates

- Two tenants (demo-clinic, demo-salon) are independent — Tenant A cannot see Tenant B bookings

- Super admin panel accessible at booking.virajdomadia.com/superadmin

- Railway logs show no errors on normal usage

DONE WHEN — all of these pass before moving to next feature

✓ Live at https://booking.virajdomadia.com — SSL cert valid, no browser warnings

✓ Full booking flow works end-to-end on real mobile at the live URL

✓ Confirmation email received within 30 seconds on the live URL

✓ Admin dashboard accessible and functional at live URL

✓ Two demo tenants are independent (RLS working in production)

✓ GitHub Actions pipeline runs green on push to main

✓ README has live demo link, setup instructions, and architecture overview

# Appendix: Dependency Map

Build strictly in this order. Starting a feature before its dependency is done will create integration bugs that take longer to fix than doing it right the first time.

| Feature | Depends On | Why you can't skip ahead |
| --- | --- | --- |
| F1 Auth | F0 | Auth middleware sets RLS context — without it, every protected route is unguarded |
| F2 Schedule | F1 | Schedule requires auth. Availability engine in F4 reads schedule directly. |
| F3 Services | F1 | Services require auth. Availability requires serviceId from F3. |
| F4 Booking Flow | F2 + F3 | Availability reads schedule. Booking creates reference to service. Both must exist. |
| F5 Admin | F4 | Admin actions (confirm/cancel) must have bookings to act on. F4 creates them. |
| F6 Emails | F4 + F5 | Email triggers fire from booking creation (F4) and status changes (F5). |
| F7 Cancel Link | F6 | Cancel link is in the confirmation email. Email must exist first. |
| F8 Staff | F1 + F6 | Staff invite sends an email. Invite accept uses auth flow from F1. |
| F9 Cron | F6 | Reminder cron sends the reminder email template built in F6. |
| F10 Super Admin | F1 | Super admin login reuses auth infrastructure from F1. |
| F11 Deploy | All | Every feature must work locally before deploying. Pipeline runs migrations. |

— End of Feature Build Guide —